## Review Summary
Mercy ASM Discovery Deliverables Review — Updated Repo Analysis
Reperformed review of the MercyASMConsult repository against the signed SOW after the latest git updates. This version supersedes the earlier pass.
Metric | Value | Updated Assessment
Total deliverables reviewed | 5 | The updated repo closes one of the biggest prior gaps: it now has a clear consolidated findings register and stronger discovery-planning artifacts. The main remaining open SOW gap is the lack of a formal future-state options package with ROM estimates and timeline ranges.
Completed | 2
Partial | 2
Open | 0
Average completion | 76.25%
Bottom line
Compared with the prior review, the repo now appears substantially complete for Current-State Assessment, Gap and Risk Register, and Executive Readout support. Discovery Workplan coverage is stronger but still not fully packaged as a working tracker. Future-State Options Summary remains the main contractual shortfall.

## Deliverables Review
Deliverables Review
ID | SOW Deliverable | Status | Completion % | Change vs Prior Review | Updated Assessment | Remaining Gap | Primary Evidence
D1 | Discovery Workplan and session schedule | Partial | 70% | Improved materially | The updated repo now includes a 4-week discovery process, weekly inputs and outcomes, working model, and working assumptions surfaced on the Kickoff page. | Still not a standalone maintained tracker or spreadsheet-style session schedule, so it does not fully meet the SOW wording as a working document. | Kickoff page plus DiscoveryProcess and DiscoveryCadence components.
D2 | Current-State Assessment Summary | Completed | 100% | No change | The repo still has strong current-state coverage across kickoff, discovery sessions, artifact analysis, and current-vs-future-state walkthroughs. | This remains one of the strongest completed deliverables in the repo. | SOW page, Kickoff, Discussion pages, ASM Analysis Current, MAO Data Gap Analysis.
D3 | Gap and Risk Register | Completed | 90% | Improved materially | The repo now has a dedicated Findings page that acts as a consolidated, de-duplicated gap and risk register with stable IDs, source traceability, and resolution lanes. | It is stronger than the prior scattered evidence, though it is findings-first rather than a classic spreadsheet register with severity/owner columns on every row. | Findings page and findings data with traceability mappings.
D4 | Future-State Options Summary with ROM and timeline ranges | Partial | 45% | No meaningful change | The updated repo still has robust submission and reconciliation recommendations and roadmaps, but not a formal options comparison with multiple alternative paths and planning-level ROM estimates. | Roadmaps are present, but the SOW asked for option-level scope, assumptions, benefits, tradeoffs, risks, sequencing, dependencies, ROM, and timeline ranges. | Submission Strategy and Reconciliation Strategy lanes.
D5 | Executive Readout materials and final recommendation summary | Completed | 95% | Improved slightly | The repo continues to show strong readout and recommendation coverage, now with additional findings traceability and MAO data-gap analysis that better supports the recommendation narrative. | This appears substantially complete from a content perspective. | Kickoff PDFs/PPTX, recommendation lanes, findings page, MAO Data Gap Analysis.

## Changes Since Prior
Changes Since Prior Review
Changed Area | What Changed | Evidence
Discovery workplan moved from Open to Partial | New kickoff timeline and cadence artifacts now document a 4-week process, Mercy inputs, and weekly outcomes. | Kickoff.tsx, DiscoveryProcess.tsx, DiscoveryCadence.tsx, replit.md
Gap and risk register moved from Partial to Completed | A dedicated Findings page now consolidates engagement findings and traces each one to source pages and resolution lanes. | Findings.tsx, findings.ts, replit.md
Future-state options summary remains Partial | The repo still does not show multiple formal option paths with ROM estimates and timeline ranges as called for in the SOW. | SubmissionStrategy.tsx, ReconciliationStrategy.tsx

## Evidence Map
Evidence Map
Evidence Area | Why It Matters | Primary File | Secondary File
Structured kickoff workplan proxy | Kickoff now includes tabs for timeline and discovery cadence, which materially improve workplan coverage. | /Volumes/ExternalData/Projects/MercyASMConsult/artifacts/engagement-portal/src/pages/Kickoff.tsx | /Volumes/ExternalData/Projects/MercyASMConsult/artifacts/engagement-portal/src/components/DiscoveryProcess.tsx
Working assumptions and cadence | The cadence component captures proposed working model and working assumptions, strengthening the planning evidence. | /Volumes/ExternalData/Projects/MercyASMConsult/artifacts/engagement-portal/src/components/DiscoveryCadence.tsx | /Volumes/ExternalData/Projects/MercyASMConsult/replit.md
Consolidated findings register | The findings page provides the clearest SOW-aligned evidence for a gap and risk register in the updated repo. | /Volumes/ExternalData/Projects/MercyASMConsult/artifacts/engagement-portal/src/pages/Findings.tsx | /Volumes/ExternalData/Projects/MercyASMConsult/artifacts/engagement-portal/src/data/findings.ts
Recommendation traceability | Recommendation lanes now link recommendations back to findings, improving readout readiness and auditability. | /Volumes/ExternalData/Projects/MercyASMConsult/artifacts/engagement-portal/src/data/traceability.ts | /Volumes/ExternalData/Projects/MercyASMConsult/replit.md