## Review Summary
Mercy ASM Discovery Deliverables Review
Review workbook comparing the signed SOW deliverables against the MercyASMConsult repository contents. Agreement signed March 11, 2026.
Metric | Value |  | Review Takeaways
Total deliverables reviewed | 5 |  | The repo is strongest on current-state assessment and future-state recommendations. The main open items are the formal SOW packaging artifacts: a workplan, a consolidated gap/risk register, and an options summary with ROM estimates and timeline ranges. | The repo is strongest on current-state assessment and future-state recommendations. The main open items are the formal SOW packaging artifacts: a workplan, a consolidated gap/risk register, and an options summary with ROM estimates and timeline ranges. | The repo is strongest on current-state assessment and future-state recommendations. The main open items are the formal SOW packaging artifacts: a workplan, a consolidated gap/risk register, and an options summary with ROM estimates and timeline ranges. | The repo is strongest on current-state assessment and future-state recommendations. The main open items are the formal SOW packaging artifacts: a workplan, a consolidated gap/risk register, and an options summary with ROM estimates and timeline ranges. | The repo is strongest on current-state assessment and future-state recommendations. The main open items are the formal SOW packaging artifacts: a workplan, a consolidated gap/risk register, and an options summary with ROM estimates and timeline ranges.
Completed | 1 |  | The repo is strongest on current-state assessment and future-state recommendations. The main open items are the formal SOW packaging artifacts: a workplan, a consolidated gap/risk register, and an options summary with ROM estimates and timeline ranges. | The repo is strongest on current-state assessment and future-state recommendations. The main open items are the formal SOW packaging artifacts: a workplan, a consolidated gap/risk register, and an options summary with ROM estimates and timeline ranges. | The repo is strongest on current-state assessment and future-state recommendations. The main open items are the formal SOW packaging artifacts: a workplan, a consolidated gap/risk register, and an options summary with ROM estimates and timeline ranges. | The repo is strongest on current-state assessment and future-state recommendations. The main open items are the formal SOW packaging artifacts: a workplan, a consolidated gap/risk register, and an options summary with ROM estimates and timeline ranges. | The repo is strongest on current-state assessment and future-state recommendations. The main open items are the formal SOW packaging artifacts: a workplan, a consolidated gap/risk register, and an options summary with ROM estimates and timeline ranges.
Partial | 2 |  | The repo is strongest on current-state assessment and future-state recommendations. The main open items are the formal SOW packaging artifacts: a workplan, a consolidated gap/risk register, and an options summary with ROM estimates and timeline ranges. | The repo is strongest on current-state assessment and future-state recommendations. The main open items are the formal SOW packaging artifacts: a workplan, a consolidated gap/risk register, and an options summary with ROM estimates and timeline ranges. | The repo is strongest on current-state assessment and future-state recommendations. The main open items are the formal SOW packaging artifacts: a workplan, a consolidated gap/risk register, and an options summary with ROM estimates and timeline ranges. | The repo is strongest on current-state assessment and future-state recommendations. The main open items are the formal SOW packaging artifacts: a workplan, a consolidated gap/risk register, and an options summary with ROM estimates and timeline ranges. | The repo is strongest on current-state assessment and future-state recommendations. The main open items are the formal SOW packaging artifacts: a workplan, a consolidated gap/risk register, and an options summary with ROM estimates and timeline ranges.
Open | 1 |  | The repo is strongest on current-state assessment and future-state recommendations. The main open items are the formal SOW packaging artifacts: a workplan, a consolidated gap/risk register, and an options summary with ROM estimates and timeline ranges. | The repo is strongest on current-state assessment and future-state recommendations. The main open items are the formal SOW packaging artifacts: a workplan, a consolidated gap/risk register, and an options summary with ROM estimates and timeline ranges. | The repo is strongest on current-state assessment and future-state recommendations. The main open items are the formal SOW packaging artifacts: a workplan, a consolidated gap/risk register, and an options summary with ROM estimates and timeline ranges. | The repo is strongest on current-state assessment and future-state recommendations. The main open items are the formal SOW packaging artifacts: a workplan, a consolidated gap/risk register, and an options summary with ROM estimates and timeline ranges. | The repo is strongest on current-state assessment and future-state recommendations. The main open items are the formal SOW packaging artifacts: a workplan, a consolidated gap/risk register, and an options summary with ROM estimates and timeline ranges.
Average completion | 57.5% |  | The repo is strongest on current-state assessment and future-state recommendations. The main open items are the formal SOW packaging artifacts: a workplan, a consolidated gap/risk register, and an options summary with ROM estimates and timeline ranges. | The repo is strongest on current-state assessment and future-state recommendations. The main open items are the formal SOW packaging artifacts: a workplan, a consolidated gap/risk register, and an options summary with ROM estimates and timeline ranges. | The repo is strongest on current-state assessment and future-state recommendations. The main open items are the formal SOW packaging artifacts: a workplan, a consolidated gap/risk register, and an options summary with ROM estimates and timeline ranges. | The repo is strongest on current-state assessment and future-state recommendations. The main open items are the formal SOW packaging artifacts: a workplan, a consolidated gap/risk register, and an options summary with ROM estimates and timeline ranges. | The repo is strongest on current-state assessment and future-state recommendations. The main open items are the formal SOW packaging artifacts: a workplan, a consolidated gap/risk register, and an options summary with ROM estimates and timeline ranges.
Recommended next review actions
1. Create a formal discovery workplan and session tracker. 2. Consolidate the scattered findings into a single gap and risk register. 3. Add a future-state options comparison with ROM estimates and indicative timing. 4. Package the existing portal content into a final client-facing deliverables bundle. | 1. Create a formal discovery workplan and session tracker. 2. Consolidate the scattered findings into a single gap and risk register. 3. Add a future-state options comparison with ROM estimates and indicative timing. 4. Package the existing portal content into a final client-facing deliverables bundle. | 1. Create a formal discovery workplan and session tracker. 2. Consolidate the scattered findings into a single gap and risk register. 3. Add a future-state options comparison with ROM estimates and indicative timing. 4. Package the existing portal content into a final client-facing deliverables bundle. | 1. Create a formal discovery workplan and session tracker. 2. Consolidate the scattered findings into a single gap and risk register. 3. Add a future-state options comparison with ROM estimates and indicative timing. 4. Package the existing portal content into a final client-facing deliverables bundle. | 1. Create a formal discovery workplan and session tracker. 2. Consolidate the scattered findings into a single gap and risk register. 3. Add a future-state options comparison with ROM estimates and indicative timing. 4. Package the existing portal content into a final client-facing deliverables bundle. | 1. Create a formal discovery workplan and session tracker. 2. Consolidate the scattered findings into a single gap and risk register. 3. Add a future-state options comparison with ROM estimates and indicative timing. 4. Package the existing portal content into a final client-facing deliverables bundle. | 1. Create a formal discovery workplan and session tracker. 2. Consolidate the scattered findings into a single gap and risk register. 3. Add a future-state options comparison with ROM estimates and indicative timing. 4. Package the existing portal content into a final client-facing deliverables bundle. | 1. Create a formal discovery workplan and session tracker. 2. Consolidate the scattered findings into a single gap and risk register. 3. Add a future-state options comparison with ROM estimates and indicative timing. 4. Package the existing portal content into a final client-facing deliverables bundle.
1. Create a formal discovery workplan and session tracker. 2. Consolidate the scattered findings into a single gap and risk register. 3. Add a future-state options comparison with ROM estimates and indicative timing. 4. Package the existing portal content into a final client-facing deliverables bundle. | 1. Create a formal discovery workplan and session tracker. 2. Consolidate the scattered findings into a single gap and risk register. 3. Add a future-state options comparison with ROM estimates and indicative timing. 4. Package the existing portal content into a final client-facing deliverables bundle. | 1. Create a formal discovery workplan and session tracker. 2. Consolidate the scattered findings into a single gap and risk register. 3. Add a future-state options comparison with ROM estimates and indicative timing. 4. Package the existing portal content into a final client-facing deliverables bundle. | 1. Create a formal discovery workplan and session tracker. 2. Consolidate the scattered findings into a single gap and risk register. 3. Add a future-state options comparison with ROM estimates and indicative timing. 4. Package the existing portal content into a final client-facing deliverables bundle. | 1. Create a formal discovery workplan and session tracker. 2. Consolidate the scattered findings into a single gap and risk register. 3. Add a future-state options comparison with ROM estimates and indicative timing. 4. Package the existing portal content into a final client-facing deliverables bundle. | 1. Create a formal discovery workplan and session tracker. 2. Consolidate the scattered findings into a single gap and risk register. 3. Add a future-state options comparison with ROM estimates and indicative timing. 4. Package the existing portal content into a final client-facing deliverables bundle. | 1. Create a formal discovery workplan and session tracker. 2. Consolidate the scattered findings into a single gap and risk register. 3. Add a future-state options comparison with ROM estimates and indicative timing. 4. Package the existing portal content into a final client-facing deliverables bundle. | 1. Create a formal discovery workplan and session tracker. 2. Consolidate the scattered findings into a single gap and risk register. 3. Add a future-state options comparison with ROM estimates and indicative timing. 4. Package the existing portal content into a final client-facing deliverables bundle.
1. Create a formal discovery workplan and session tracker. 2. Consolidate the scattered findings into a single gap and risk register. 3. Add a future-state options comparison with ROM estimates and indicative timing. 4. Package the existing portal content into a final client-facing deliverables bundle. | 1. Create a formal discovery workplan and session tracker. 2. Consolidate the scattered findings into a single gap and risk register. 3. Add a future-state options comparison with ROM estimates and indicative timing. 4. Package the existing portal content into a final client-facing deliverables bundle. | 1. Create a formal discovery workplan and session tracker. 2. Consolidate the scattered findings into a single gap and risk register. 3. Add a future-state options comparison with ROM estimates and indicative timing. 4. Package the existing portal content into a final client-facing deliverables bundle. | 1. Create a formal discovery workplan and session tracker. 2. Consolidate the scattered findings into a single gap and risk register. 3. Add a future-state options comparison with ROM estimates and indicative timing. 4. Package the existing portal content into a final client-facing deliverables bundle. | 1. Create a formal discovery workplan and session tracker. 2. Consolidate the scattered findings into a single gap and risk register. 3. Add a future-state options comparison with ROM estimates and indicative timing. 4. Package the existing portal content into a final client-facing deliverables bundle. | 1. Create a formal discovery workplan and session tracker. 2. Consolidate the scattered findings into a single gap and risk register. 3. Add a future-state options comparison with ROM estimates and indicative timing. 4. Package the existing portal content into a final client-facing deliverables bundle. | 1. Create a formal discovery workplan and session tracker. 2. Consolidate the scattered findings into a single gap and risk register. 3. Add a future-state options comparison with ROM estimates and indicative timing. 4. Package the existing portal content into a final client-facing deliverables bundle. | 1. Create a formal discovery workplan and session tracker. 2. Consolidate the scattered findings into a single gap and risk register. 3. Add a future-state options comparison with ROM estimates and indicative timing. 4. Package the existing portal content into a final client-facing deliverables bundle.
1. Create a formal discovery workplan and session tracker. 2. Consolidate the scattered findings into a single gap and risk register. 3. Add a future-state options comparison with ROM estimates and indicative timing. 4. Package the existing portal content into a final client-facing deliverables bundle. | 1. Create a formal discovery workplan and session tracker. 2. Consolidate the scattered findings into a single gap and risk register. 3. Add a future-state options comparison with ROM estimates and indicative timing. 4. Package the existing portal content into a final client-facing deliverables bundle. | 1. Create a formal discovery workplan and session tracker. 2. Consolidate the scattered findings into a single gap and risk register. 3. Add a future-state options comparison with ROM estimates and indicative timing. 4. Package the existing portal content into a final client-facing deliverables bundle. | 1. Create a formal discovery workplan and session tracker. 2. Consolidate the scattered findings into a single gap and risk register. 3. Add a future-state options comparison with ROM estimates and indicative timing. 4. Package the existing portal content into a final client-facing deliverables bundle. | 1. Create a formal discovery workplan and session tracker. 2. Consolidate the scattered findings into a single gap and risk register. 3. Add a future-state options comparison with ROM estimates and indicative timing. 4. Package the existing portal content into a final client-facing deliverables bundle. | 1. Create a formal discovery workplan and session tracker. 2. Consolidate the scattered findings into a single gap and risk register. 3. Add a future-state options comparison with ROM estimates and indicative timing. 4. Package the existing portal content into a final client-facing deliverables bundle. | 1. Create a formal discovery workplan and session tracker. 2. Consolidate the scattered findings into a single gap and risk register. 3. Add a future-state options comparison with ROM estimates and indicative timing. 4. Package the existing portal content into a final client-facing deliverables bundle. | 1. Create a formal discovery workplan and session tracker. 2. Consolidate the scattered findings into a single gap and risk register. 3. Add a future-state options comparison with ROM estimates and indicative timing. 4. Package the existing portal content into a final client-facing deliverables bundle.

## Deliverables Review
Deliverables Review
ID | SOW Deliverable | Reference | Repo Status | Completion % | Assessment | Repo Evidence | Recommended Next Step
D1 | Discovery Workplan and session schedule | SOW Section 3 | Open | 20% | Kickoff planning context exists in the portal, but no formal workplan or maintained schedule artifact was found. | KickoffPlanning page; kickoff notes; discovery discussion artifacts. | Create a standalone workplan workbook or schedule tracker with sessions, dates, participants, requested artifacts, and status.
D2 | Current-State Assessment Summary | SOW Section 3 | Completed | 100% | Strong current-state coverage exists across kickoff, artifact analysis, current/future-state walkthroughs, and discussion summaries. | Phase1, Kickoff, DiscussionJun08, DiscussionJun10, DiscussionJun12, DiscussionJun17, HpLayoutSql, attached SQL/layout/source artifacts. | Package the existing material as a named final assessment document if Mercy wants a single-file deliverable.
D3 | Gap and Risk Register | SOW Section 3 | Partial | 65% | Gaps and risks are documented throughout the portal and recommendation packets, but not as one consolidated register. | Phase1 risk/deliverables sections; Submission Strategy register; Reconciliation Strategy register; June 12 and June 17 findings. | Create a dedicated register with severity, impact, mitigation, owner, and disposition.
D4 | Future-State Options Summary with ROM and timeline ranges | SOW Section 3 | Partial | 45% | Future-state recommendations are well developed, but the repo does not show a formal options matrix with multiple option paths and planning-level ROM estimates. | Submission Strategy and Reconciliation Strategy packets; future-state architecture and roadmap content. | Add an options sheet with incremental vs broader transformation paths, tradeoffs, dependencies, ROM estimates, and indicative timing.
D5 | Executive Readout materials and final recommendation summary | SOW Section 3 | Completed | 90% | Readout-style materials and recommendation packets are present, including kickoff/future-state decks and the portal recommendation pages. | MercyKickoff deck, MercyFutureState PDF, Submission Strategy page, Reconciliation Strategy page, recommendation packet source workbooks. | Optionally assemble a final executive deck/package that mirrors the SOW naming one-to-one.

## Evidence Map
Evidence Map
Evidence Area | What It Supports | Primary File / Folder | Secondary File / Folder
Portal routes and navigation | The portal includes routes for SOW, kickoff, discussion dates, current-state analysis, submission strategy, and reconciliation strategy. | /Volumes/ExternalData/Projects/MercyASMConsult/artifacts/engagement-portal/src/App.tsx | /Volumes/ExternalData/Projects/MercyASMConsult/artifacts/engagement-portal/src/components/layout/Sidebar.tsx
Current-state and artifact analysis | The current-state review is supported by a dedicated ASM artifacts analysis page and multiple discovery discussion pages. | /Volumes/ExternalData/Projects/MercyASMConsult/artifacts/engagement-portal/src/pages/HpLayoutSql.tsx | /Volumes/ExternalData/Projects/MercyASMConsult/artifacts/engagement-portal/src/pages/DiscussionJun12.tsx
Submission recommendation packet | The submission path recommendation is implemented as a full packet with executive overview, register, blueprint, governance, QA, roadmap, and sources. | /Volumes/ExternalData/Projects/MercyASMConsult/artifacts/engagement-portal/src/pages/SubmissionStrategy.tsx | /Volumes/ExternalData/Projects/MercyASMConsult/artifacts/engagement-portal/src/data/submissionStrategy.ts
Reconciliation recommendation packet | The reconciliation path recommendation is implemented as a full packet with intake, MAO analytics, root cause, controls, roadmap, and sources. | /Volumes/ExternalData/Projects/MercyASMConsult/artifacts/engagement-portal/src/pages/ReconciliationStrategy.tsx | /Volumes/ExternalData/Projects/MercyASMConsult/artifacts/engagement-portal/src/data/reconciliationStrategy.ts
Source decks and workbooks | The repo includes kickoff decks, future-state PDFs, SQL samples, layout files, and source recommendation workbooks used to prepare the portal content. | /Volumes/ExternalData/Projects/MercyASMConsult/attached_assets | /Volumes/ExternalData/Projects/MercyASMConsult/replit.md